## Revision Sheet
Project Name
Project Plan
Revision History
Version | Date | Updates/Changes | Reviewed by | Confirmed by

## Project Information
Project Name
Project Plan
Project Details
Project Name |  | MoneyTor
Project Description |  | This is a software to be made as a partial requirement
for the <CS/IT140> Software Engineering class. The software that the team
shall develop will apply the process of project management. This
Software <continue>
Project Team
| Project Leader | Trisha Jean Lim (limtrishajean@gmail.com)
| Project Members |  | Sonia Margarette Vidal
Joseph Gabriell Palmaras
Daniel Kenneth Sandimas
Ivan Wesley Chua
Software Process Model |  | Waterfall Model combined with Incremental and Iterative
Project Scope |  | Major Software Functionalities
*ACCOUNT PAYABLES
*ACCOUNT RECEIVABLES
*RECEIPT INFORMATION
*DEBT NOTIFICATIONS
*SUMMARY REPORTS
*USER AUTHENTICATION
Deliverables
* Project Proposal
* Project Plan
* Meeting Minutes
* Weekly Progress Reports
* Review Record Cards
* Requirements Specification
* Design Documents
* Coding Guidelines
* Source Codes
* Unit Testing Specifications
* Unit Testing Results
* Integration Testing Specifications
* Integration Testing Results
* Release Notes
*Installation Manual
* Working Software
* Project Completion Report
Note on D12: Include email addresses

## Assumption_Constraints_Risks
Project Name
Project Plan
Assumptions
* | The programmers are already familiar with the programming language they will use.
* | Tools and other equipments needed are available.
* | Number of members in the team are fixed all throughout the software engineering process.
* | Team members can render over time work if the need arises.
* | Payment of resources will be shared by all members of the team.
Constraints
* | Size of the team is fixed. Hence, no additional members may be recruited during the course of the software development.
Risks
Risk |  | Preventive Action/s | Countermeasure/s
* | Time of the students is consumed by their other subjects. | Members should follow the agreed number of | Overtime will be rendered if slippage to schedule
|  | hours to be allocated to the project. | occurs.
* | The Project Room cannot be available for use. | Coordinate with the Lab Head or the working scholars when using the room | Bring a laptop with completely installed tools for project making.
* | Funds diverted to other projects | Project leader will see to it that the team is still aligned with the budget schedule. | All team members will contribute for additional monetary resources.
Note on D16: Abalquin: Actions to be done to prevent the risk from occurring.
Note on E16: Abalquin: Action to do when a risk becomes an issue to lessen its impact to the project.

## Roles and Responsibilites
Project Name
Project Plan
Roles Assignment
* | Project Coordinator | Erwin Sarmiento
* | Project Leader | Trisha Jean Lim
* | Assistant Project Leader | Sonia Margarette Vidal
* | Minutes Recorder | Joseph Gabriell Palmaras
* | Librarian | Daniel Kenneth Sandimas
* | Configuration In-charge | Ivan Wesley Chua
* | Developers | ALL TEAM MEMBERS
* | Tester/s | ALL TEAM MEMBERS
Responsibility Assignment Matrix (RAM)
Role/Responsibilities |  | Project Planning | Requirements Dev't | Design, Implementation, Testing | Project Monitoring and Control
* | Project Coordinator | Reviews and approves each version of the Project Plan and Schedule. | Reviews and approves each version of the Requirements Specification. | Checks the coding guidelines. Conducts design and code reviews | Checks Weekly Progress Report and Meeting Minutes. Checks for possible risks on a weekly basis.
Performs Process Audit
| Project Leader | Drives the creation, review and confirmation each version of the Project Plan and Schedule. | Drives the creation, review and confirmation each version of the Requirements Specification. | Spearheads creation of coding guidelines. Spearheads review of design documents and test cases for unit testing and internal testing/system testing. Spearheads initial code reviews. Approves the design document and codes. | Monitors and tracks status of tasks assigned. Conducts Weekly Progress Meeting. Prepares the Weekly Progress Report. Presents the Weekly Progress Report to class on a weekly basis. Monitors bug status until completion. Calls an emergency meeting when issues are encountered.
Collects, reviews and summarizes the process metrics.
* | Assistant Project Leader | Supports the creation, review and confirmation each version of the Project Plan and Schedule. | Supports creation, review and confirmation of each version of the Requirements Specification. | Assists creation of coding guidelines. Assists review of design documents and test cases for unit testing and internal testing/system testing. Assists/spearheads code reviews. | Assists and monitors developers on the technical issues of their respective modules.
Collects, reviews and summarizes the process metrics.
* | Minutes Recorder | Creates Meeting Minutes during the Project Planning meetings and reviews. | Creates Meeting Minutes during the Requirements Development meetings and reviews. | Creates Meeting Minutes for implementation activities meetings and reviews. | Creates Meeting Minutes during Weekly Progress Meeting and emergency meetings.
Submits time spent in Meeting Minutes Recording to the Project Leader.
* | Librarian | Checks if the versioning and the updates of the Project Plan are stored and kept tracked. Drives the creation of folder structure of the project. Registers documents related to this phase. Formulates the DM Plan. Submits a monthly library inventory report to the project coordinator. | Checks if the versioning and the updates of the Requirements Specification are stored and kept tracked. Registers documents related to this phase. Submits a monthly library inventory report to the project coordinator. | Checks if the versioning and the updates of the test specification and results are stored and kept tracked. Stores Release Notes for Alpha and Final Release. Registers documents related to this phase. Submits a monthly library inventory report to the project coordinator. | Reminds the team on document-related processes, if necessary. Checks if all document versioning and template items are filled-up. Registers documents related to this phase. Submits a monthly library inventory report to the project coordinator.
Submits time spent in Data Management to the Project Leader.
* | Configuration In-charge | Discuss with the team process of coding guidelines, structure, and integration. Discuss with the team process of database guidelines. Formulates the CM Plan. | Supports creation, review and confirmation of each version of the Requirements Specification. | Makes sure that the code integration process is followed. Manages the database. Prepares the build for unit and integration testing activities. Prepares Release Notes for Alpha and Final Release. Release the software. | Reminds the team on configuration processes, if necessary. Checks if all document versioning and template items are filled-up.
Submits time spent in Configuration Management to the Project Leader.
* | Developer | Supports creation, review and confirmation of each version of the Project Plan and Schedule. | Supports creation, review and confirmation of each version of the Requirements Specification. | Does design, coding, unit testing. Supports design, code and test cases review. Prepares unit testing test cases and performs unit testing. Fixes bugs. | Attends Weekly Progress Meetings and emergency meetings. Reports issues to the Project Leader (e.g. Task delayed, technical issues, etc.) Reports possible risk/s. Reports status of the assigned task to the Project Leader.
Submits the time spent in doing implementation-related activities to the Project Leader.
* | Tester/s | Reviews and confirms each version of Project Plan and Schedule. | Reviews and confirms the Requirements Specification. | Prepares the test cases, performs internal testing and do checking of the bug fixed. Note: Internal testing can be done in one OS or platform only. Reviews and confirms the design document and codes. Reports bugs. Checks fixed bugs. | Attends Weekly Progress Meetings and emergency meetings. Reports internal testing issues to the Project Leader (e.g. Task delayed, issues, etc.) Reports possible risk/s. Reports status of testing.
Submits the time spent in doing testing-related activities to the Project Leader.
Note on C18: Abalquin: You may revise the responsibilities for each role as it applies to your team.
Note on F19: Abalquin: Includes design, coding, unit testing, internal testing and system testing.

## Resources
MoneyTor
Project Plan
Resources Needed
Item | Cost
5 laptops | 178000
Fare | 3000
Snacks | 5000
Internet | 20000
Bondpaper | 500
Yellow/white paper | 20
Adobe Photoshop
Eclipse | 0
Apache Tomcat | 0
MS Office (Excel, Word, Powerpoint)
GitHub | 0
Slack | 0
Facebook | 0
Google Chrome | 0
Total Cost | 206520

## Document Management
Project Name
Project Plan
Data Management
Main Location of the Documents | XXX's laptop, stored in Drive E:\mario newinters\softeng with the folder name "Digital Organizer"
Backup Location | Every member's laptop and PC in the department's project room
Document Registration Procedure | 1. Request for template of the document should be sent to the Librarian via email to the Project Coordinator.
2. After creation of the document and before it is scheduled for review, Librarian stores official version to the library.
3. Librarian emails to Project Leader CC the team and Project Coordinator that he/she has stored the document to the library with official filename
4. After document is modified based on review, Librarian stores modified version to the library.
5. Librarian should notify Project Coordinator for succeeding versions of the document after it is already confirmed before storing to the library.
Filename Naming Convention | Format: | ProjectName_DocumentName_VersionNumber
If more than one word, capitalize the first letter of the word. If more than one word, don't separate the ProjectName with underscore. If more than one word, separate DocumentName with underscore.
| Examples: | DigitalOrganizer_Requirements_Specification_v1.00
Folder Structure | 00_Pre-development
Project Proposal
| 01_Project Planning | 02_Project Planning
Project_Plan
Review Record Card
02_Requirements Specification
Requirements_Specification
Review Record Card
03_Design
General Design (Activity, Class, Sequence, Software Archi)
DB Design
ScreenDef
Review Record Card
| 04_Coding | 02_Project Planning
Coding Guidelines
Review Record Card (from APL)
Unit Testing Specifications (blank, not yet filled up)
Integration Testing Specifications (blank, not yet filled up)
05_Testing
Unit Testing Results (filled up UTS)
UT Bug Report
Integration Testing Results (filled up ITS of own software)
IT Bug Report (own software)
| 06_Release | 02_Project Planning
Internal Release Notes (3)
Alpha Release Notes
Beta Release Notes
Installation Manual
07_Project Monitoring
Meeting Minutes
Weekly Progress Report
UT Status Monitoring
IT Status Monitoring (own software)
| 08_Project Closure | 02_Project Planning
Project Completion Report
01_Meeting Minutes
02_Weekly Progress Report
02_Project Planning
Email Structure Template | Subject: | Precede the subject [CS140] with the process where it belongs:
[PLANNING] <Subject> Document Request/Document Registration
[REQ] <Subject> Document Request/Document Registration
[DESIGN] <Subject> Document Request/Document Registration
[CODING] <Subject> Document Request/Document Registration
[UNIT_TESTING] <Subject> Document Request/Document Registration
[INTEGRATION_TESTING] <Subject> Document Request/Document Registration
[REVIEW] <Subject> Document Request/Document Registration
[PMC] <Subject> Document Request/Document Registration
[OTHERS] <Subject> Document Request/Document Registration
| Deadline: | Date of submission of the action items.

## Configuration Management
Project Name
Project Plan
Data Management
Main Location of the Source Codes and Database | GitHub Online Repository stored in https://github.com/TV5/MoneyTor
Backup Location | Every member's laptop and PC in the department's project room
Code Integration Procedure | 1. Code integration is made every Friday.
2. Before test cases are applied, testing is done only by error troubleshooting and assuring that the functionality works as expected.
3. The code for every release is stored separately from its older version. Folder naming is followed properly.
4. A team meeting will be conducted after every release for discussions and clarifications.
Filename Naming Convention | Format: | ProjectName_DocumentName
If more than one word, capitalize the first letter of the word. If more than one word, don't separate the ProjectName with underscore. If more than one word, separate DocumentName with underscore.
| Examples: | DigitalOrganizer_alarm_setting.java
Database Management Guidelines | 1. CM should be aware of all changes made to the database.
2. DB backup is performed every Friday
Email Structure Template | Subject: | Precede the subject with the process where it belongs:
[PLANNING] <Subject>
[REQ] <Subject>
[DESIGN] <Subject>
[CODING] <Subject>
[INT_TESTING] <Subject>
[SYS_TESTING] <Subject>
[DATA_CM] <Subject
[PMC] <Subject>
[OTHERS] <Subject>
| Deadline: | Date of submission of the action items.

## PMC
Project Name
Project Plan
Project Monitoring and Control
Weekly Progress Meeting Schedule | Every Saturday at 12:00 - 12:30pm
Weekly Progress Submission | Every Monday night before 12MN.
Weekly Progress Submission In-charge | TRISHA JEAN LIM or in her unavailability, SONIA MARGARETTE VIDAL
Monthly Meeting Minutes Submission | Every 5th of the month
Monthly Meeting Minutes Submission In-charge | JOSEPH GABRIELL PALMARAS or in his unavailability, TRISHA JEAN LIM